## Summary - MH
KIE Benchmark Estimate
Honoapiilani Highway Improvements ¦ 02.09.2026
Discipline | Account Codes | Quantity Description | Key Quantities | Unit | Benchmark MH | Benchmark MH (Custom) | Bottoms Up MH | Notes | Benchmark Production | Benchmark Production (Custom) | Bottoms Up Production
Digital Engineering | 88.40.26 | Anticipated Contract Amount | 300000 | K$ | 6643 | 6643 |  | Assumed medium complexity, 24 months base design duration | 0.022143 | 0.022143 | 0
Drainage | 88.40.27 | Project Area | 121.5 | AC | 18013.6393 | 14250.5869 |  | Custom: SEC 820, I-15, I-17, US 97, 264th | 148.2604 | 117.2888 | 0
Environmental | 88.40.39 | Permit Count | 12 | EA | 4200 | 4200 |  | Benchmark uses SEC 820 production of 350 MH/EA | 350 | 350 | 0
MOT | 88.40.37 | Roadway Alignment Length | 34910 | LF | 10529.5324 | 8563.4357 |  | Custom: SEC 820, I-15, I-17, US 97, 264th | 0.30162 | 0.2453 | 0
Roadway (Civil) | 88.40.47, 88.40.39 | Roadway Alignment Length | 34910 | LF | 15829.0438 | 20396.745 |  | Custom: SEC 820, I-15, I-17, US 97, 264th, 30 Crossing | 0.45342 | 0.58427 | 0
Traffic | 88.40.65 | Roadway Alignment Length | 34910 | LF | 9673.1929 | 7882.0406 |  | Custom: SEC 820, I-15, I-17, US 97, 264th, 30 Crossing | 0.27709 | 0.22578 | 0
Utilities | 88.40.67 | Self-Perform Design Relocations | 15 | EA | 3802.7994 | 3719.6299 |  | Custom: SEC 820, I-15, US 97, 264th | 253.52 | 247.9753 | 0
Walls (Total) | 88.40.69 | Wall Area | 10310 | SF | 433.0538 | 473.4034 |  | Custom: SEC 820, I-15, 30 Crossing, US 97 - All retaining walls, no sound walls | 0.042003 | 0.045917
Retaining Walls | 88.40.69 (includes Roadway and Structures, excludes Geotech) | Retaining Wall Area | 10310 | SF | 433.0538 | 473.4034 |  | Custom: SEC 820, I-15, 30 Crossing, US 97 | 0.042003 | 0.045917 | 0
Noise Walls | 88.40.69 (includes Roadway and Structures, excludes Geotech) | Noise Wall Area |  | SF | 0 | 0 |  | Benchmark: SEC 820
Bridges (Total) | 88.45.81 (excludes MSTR) | Bridge Deck Area | 226140 | SF | 21240.221 | 21240.221 |  | All PC Girder - Benchmark based on I-15, I-17, SEC 820, US 97 PC bridges | 0.093925 | 0.093925 | 0
Bridges (Vehicle - PC Girder - Single Span) | 88.45.81 (excludes MSTR) | Bridge Deck Area | 50390 | SF | 16524.296 | 16524.296 |  | Benchmark based on I-15, I-17, SEC 820, US 97 PC single span bridges | 0.32793 | 0.32793 | 0
Bridges (Vehicle - PC Girder - Multi Span) | 88.45.81 (excludes MSTR) | Bridge Deck Area | 175750 | SF | 4715.925 | 4715.925 |  | Benchmark based on I-15, I-17, SEC 820, PC multi span bridges | 0.026833 | 0.026833 | 0
Misc Structures | 88.45.81.036 | RDWY, DRA and TRF MHR | 42529.3725 | MHR | 2726.7831 | 2032.8413 |  | Custom: SEC 820, I-15, I-17, 264th | 0.064115 | 0.047799 | 0
Geotechnical | 88.50 (includes Retaining Walls) | Transportation Structure Count | 12 | EA | 5787.0806 | 2492.4014 |  | Custom: SEC 820, I-15, I-17, US 97 | 482.2567 | 207.7001 | 0
Systems | 88.35 | Track Alignment Length | 0 | TF | 0 | 0 |  | No track work anticipated in SOW
Track | 88.40.63 | Track Alignment Length | 0 | TF | 0 | 0 |  | No systems work anticipated in SOW
[OTHER DISCIPLINE] | [7 empty] | Non-Benchmarked Discipline
[OTHER DISCIPLINE] | [7 empty] | Non-Benchmarked Discipline
ESDC |  | Anticipated Project Cost | 260869.5652 | K$ | 12483.2564 | 13493.4603 |  |  | 0.047852 | 0.051725 | 0
TSCD |  | Anticipated Project Cost | 260869.5652 | K$ | 4068.3218 | 4619.8317 |  |  | 0.015595 | 0.017709 | 0
|  | Totals |  |  | 115429.9246 | 110007.5972 | 0

## DIG_DEL
Digital Engineering
eQTY: Anticipated Contract Amount
Design Management - Project Risk Assessment | [6 empty] | User Inputs
Size |  | Complexity |  |  |  |  | Job Size (Total Job Value) |  | 300000000
Value | Score | Low | Low-Med | Med | Med-High | High | Complexity Group |  | Med
<$100M | 1 | 1 | 2 | 4 | 8 | 16 | Complexity Score |  | 12
$100M - $200M | 2 | 2 | 4 | 8 | 16 | 32 | Design Duration (Months) |  | 30
$200M - $400M | 3 | 3 | 6 | 12 | 24 | 48 | Digital Delivery - Design Fee Manhours |  | 6643
$400M - $700M | 6 | 6 | 12 | 24 | 48 | 96
$700M - $1B | 10 | 10 | 20 | 40 | 80 | 160
>$1B | 12 | 12 | 24 | 48 | 96 | 192 | WBS | Description | % of Estimate MH | Benchmark MH
[7 empty] | 1.1.4 | Digital Delivery | - | -
Digital Delivery - Project Staffing Plan | [6 empty] | 1.1.4.1 | Production Management | 22% | 1461.46
PRA Score | 1 | 2 | 3 to 6 | 7 to 12 | 13 to 48 | >48 | 1.1.4.2 | Lead Responsibilities / BIM Mgmt | 25% | 1660.75
Digital Delivery Staff | 0.25 | 0.5 | 1 | 1.5 | 1.6 | 1.75 | 1.1.4.3 | Existing Conditions & Survey | 33% | 2192.19
Digital Delivery Sponsor | - | - | - | 0.1 | 0.15 | 0.25 | 1.1.4.4 | CAD Management | 20% | 1328.6
[7 empty] | 1.1.4.5 | BIM / CIM / VDC (Unique Client Rqmts) | - | -
Design Duration (Months) | Digital Delivery - Design Fee Manhours
6 | 260 | 519 | 1308 | 1661 | 1817 | 2076
7 | 303 | 606 | 1211 | 1938 | 2119 | 2422
8 | 348 | 692 | 1384 | 2214 | 2422 | 2768
9 | 389 | 779 | 1557 | 2491 | 2725 | 3114
10 | 433 | 865 | 1730 | 2768 | 3028 | 3460 |  | Start Date | 4625300%
11 | 476 | 952 | 1903 | 3045 | 3330 | 3806 |  | End Date | 4717500%
12 | 519 | 1038 | 2076 | 3322 | 3633 | 4152 |  |  | 922 | days
13 | 562 | 1125 | 2249 | 3598 | 3936 | 4498 |  |  | 131.7143 | weeks
14 | 606 | 1211 | 2422 | 3875 | 4239 | 4844 |  |  | 30.419 | monhts
15 | 649 | 1298 | 2595 | 4152 | 4541 | 5190
16 | 692 | 1384 | 2768 | 4429 | 4844 | 5536
17 | 735 | 1471 | 2941 | 4706 | 5147 | 5882
18 | 779 | 1557 | 3114 | 4982 | 5450 | 6228
19 | 822 | 1644 | 3287 | 5259 | 5752 | 6574
20 | 865 | 1730 | 3460 | 5536 | 6055 | 6920
21 | 908 | 1817 | 3633 | 5813 | 6358 | 7266
22 | 952 | 1903 | 3806 | 6090 | 6661 | 7612
23 | 995 | 1990 | 3979 | 6366 | 6963 | 7958
24 | 1038 | 2076 | 4152 | 6643 | 7266 | 8304

## DRN
Drainage Design
eQTY: Project Area (Acres)
Project | FCT MHRs | eQTY | Unit | Production | Applicable Job | Custom
IH 820 Southeast Connector | 141161 | 872 | AC | 161.8819 | Yes | 161.8819
BC Highway 1 | 2209 | 3.3 | AC | 669.3939
BC Highway 5 | 4948 | 16 | AC | 309.25
Federal Way Link Extension | 122527 | 104 | AC | 1178.1442
Foothill Phase 2A LRT | 7420 | 133 | AC | 55.7895
Foothill Phase 2B1 LRT | 72738 | 119 | AC | 611.2437
I-15 Tropicana | 14493 | 194 | AC | 74.7062 | Yes | 74.7062
I-17 Anthem | 47947 | 2171 | AC | 22.0852 | Yes | 22.0852
Ottawa LRT | 11503 | 560 | AC | 20.5411
US 97 | 7787 | 33 | AC | 235.9697 | Yes | 235.9697
264th Street Interchange | 11783 | 193 | AC | 61.0518 | Yes | 61.0518
Productions (Project Qty) |  | 121.5 | AC | 148.2604 |  | 117.2888
Input / Output
Key Quantity (Column D) | 121.5
Total MHR (All Projects) | 18013.6393
Total MHR (Custom Projects) | 14250.5869
|  |  |  | Open | Custom
| Average | 309.0961 |  | 1665.9222 | 766.397
| Standard Dev. | 367.3745 |  | -0.504 | -0.39106

## MOT
Maintenance of Traffic (MOT) Design
eQTY: Alignment Length (LF)
Project | FCT MHRs | eQTY | Unit | Production | Applicable Job | Custom
IH 820 Southeast Connector | 170668 | 550674 | LF | 0.30993 | Yes | 0.30993
BC Highway 1 | 3645 | 1120 | LF | 3.2545
BC Highway 5 | 1050 | 2300 | LF | 0.45652
Federal Way Link Extension | 32305 | 83559 | LF | 0.38661
Foothill Phase 2A LRT | 3500 | 25667 | LF | 0.13636
Foothill Phase 2B1 LRT | 7873 | 17105 | LF | 0.46027
I-15 Tropicana | 11263 | 48206 | LF | 0.23364 | Yes | 0.23364
I-17 Anthem | 13867 | 325987 | LF | 0.042539 | Yes | 0.042539
Ottawa LRT | 72414 | 547047 | LF | 0.13237
US 97 | 7364 | 107830 | LF | 0.068293 | Yes | 0.068293
264th Street Interchange | 25407 | 51920 | LF | 0.48935 | Yes | 0.48935
Productions (Project Qty) |  | 34910 | LF | 0.30162 |  | 0.2453
Input / Output
Key Quantity (Column D) | 34910
Total MHR (All Projects) | 10529.5324
Total MHR (Custom Projects) | 8563.4357
|  |  |  | Open | Custom
| Average | 0.54276 |  | 21.6563 | 6.6225
| Standard Dev. | 0.91397 |  | -0.40857 | -0.31506

## RDWY
Roadway Design
eQTY: Alignment Length (LF)
Project | FCT MHRs | eQTY | Unit | Production | Applicable Job | Custom
IH 820 Southeast Connector | 133332 | 550674 | LF | 0.24213 | Yes | 0.24213
BC Highway 1 | 4556 | 1120 | LF | 4.0679
BC Highway 5 | 6097 | 2300 | LF | 2.6509
Federal Way Link Extension | 74720 | 165248 | LF | 0.45217
Foothill Phase 2A LRT | 13279 | 180566 | LF | 0.073541
Foothill Phase 2B1 LRT | 58164 | 120338 | LF | 0.48334
I-15 Tropicana | 24245 | 48206 | LF | 0.50295 | Yes | 0.50295
I-17 Anthem | 53211 | 325987 | LF | 0.16323 | Yes | 0.16323
Ottawa LRT | 192084 | 556235 | LF | 0.34533
Tijuana River Barrier | 547 | 2807 | LF | 0.19487
30 Crossing | 40907 | 57768 | LF | 0.70813 | Yes | 0.70813
CHPE Transmission | 3410 | 23450 | LF | 0.14542
US 97 | 21330 | 102183 | LF | 0.20874 | Yes | 0.20874
264th Street Interchange | 26964 | 51920 | LF | 0.51934 | Yes | 0.51934
Productions (Project Qty) |  | 34910 | LF | 0.45342 |  | 0.58427
Input / Output
Key Quantity (Column D) | 34910
Total MHR (All Projects) | 15829.0438
Total MHR (Custom Projects) | 20396.745
|  |  |  | Open | Custom
| Average | 0.76842 |  | 14.4345 | 62.9086
| Standard Dev. | 1.1463 |  | -0.33082 | -0.44731

## TRF
Traffic Design
eQTY: Alignment Length (LF)
Project | FCT MHRs | eQTY | Unit | Production | Applicable Job | Custom
IH 820 Southeast Connector | 43833 | 550674 | LF | 0.079599 | Yes | 0.079599
Federal Way Link Extension | 42037 | 83559 | LF | 0.50308
Foothill Phase 2A LRT | 4284 | 25667 | LF | 0.16691
Foothill Phase 2B1 LRT | 12410 | 17105 | LF | 0.72552
I-15 Tropicana | 27602 | 48206 | LF | 0.57258 | Yes | 0.57258
I-17 Anthem | 12223 | 325987 | LF | 0.037495 | Yes | 0.037495
30 Crossing | 18882 | 57768 | LF | 0.32686 | Yes | 0.32686
US 97 | 1803 | 102183 | LF | 0.017645 | Yes | 0.017645
264th Street Interchange | 5649 | 51920 | LF | 0.1088 | Yes | 0.1088
Productions (Project Qty) |  | 34910 | LF | 0.27709 |  | 0.22578
Input / Output
Key Quantity (Column D) | 34910
Total MHR (All Projects) | 9673.1929
Total MHR (Custom Projects) | 7882.0406
|  |  |  | Open | Custom
| Average | 0.28205 |  | 415.7961 | 226.6415
| Standard Dev. | 0.26123 |  | -0.69916 | -0.66073

## UTL
Utilities Design (no coordination time included)
eQTY: Relocation Count (EA)
Project | FCT MHRs | eQTY | Unit | Production | Applicable Job | Custom
IH 820 Southeast Connector | 108899 | 384 | EA | 283.5911 | Yes | 283.5911
Foothill Phase 2B1 LRT | 18896 | 70 | EA | 269.9429
I-15 Tropicana | 6374 | 48 | EA | 132.7917 | Yes | 132.7917
US 97 | 3336 | 11 | EA | 303.2727 | Yes | 303.2727
264th Street Interchange | 1465 | 5 | EA | 293 | Yes | 293
Productions (Project Qty) |  | 15 | EA | 253.52 |  | 247.9753
Input / Output
Key Quantity (Column D) | 15
Total MHR (All Projects) | 3802.7994
Total MHR (Custom Projects) | 3719.6299
|  |  |  | Open | Custom
| Average | 256.5197 |  | 276.9128 | 276.9247
| Standard Dev. | 70.2466 |  | -0.032592 | -0.040773

## RWAL
Retaining Wall Design
eQTY: Wall Area (SF)
Project | FCT MHRs | eQTY | Unit | Production | Applicable Job | Custom
IH 820 Southeast Connector | 48960 | 1169432 | SF | 0.041866 | Yes | 0.041866
Federal Way Link Extension | 54751 | 434037 | SF | 0.12614
Foothill Phase 2B1 LRT | 18592 | 377619 | SF | 0.049235
I-15 Tropicana | 4724 | 95796 | SF | 0.049313 | Yes | 0.049313
30 Crossing | 3905 | 42336 | SF | 0.092238 | Yes | 0.092238
US 97 | 696 | 30039 | SF | 0.02317 | Yes | 0.02317
Productions (Project Qty) |  | 10310 | SF | 0.042003 |  | 0.045917
Input / Output
Key Quantity (Column D) | 10310
Total MHR (All Projects) | 433.0538
Total MHR (Custom Projects) | 473.4034
|  |  |  | Open | Custom
| Average | 0.063661 |  | 0.017334 | 0.046252
| Standard Dev. | 0.038077 |  | 0.095778 | -0.00078693

## NWAL
Noise Wall Design
eQTY: Wall Area (SF)
Project | FCT MHRs | eQTY | Unit | Production | Applicable Job | Custom
IH 820 Southeast Connector | 10909 | 190048 | SF | 0.057401 | Yes | 0.057401
Foothill Phase 2B1 LRT | 5339 | 241020 | SF | 0.022152 | Yes | 0.022152
Productions (Project Qty) |  | 0 | SF | 0 |  | 0
Input / Output
Key Quantity (Column D) | 0
Total MHR (All Projects) | 0
Total MHR (Custom Projects) | 0
|  |  |  | Open | Custom
| Average | 0.039776 |  | 8.1853e+19 | 8.1853e+19
| Standard Dev. | 0.024925 |  | -4.0073 | -4.0073

## STR
Bridge Structures
eQTY: Bridge Deck Area (SF)
Project | Structure Name | FCT MHRs | eQTY | Unit | Production | Applicable Job | Custom | Type | Span Arrangement | Scope
IH 820 Southeast Connector | Bridge 036 | 3389 | 240178 | SF | 0.01411 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 037 | 7087 | 199692 | SF | 0.03549 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 047 | 4409 | 143290 | SF | 0.03077 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 025 | 5202 | 136169 | SF | 0.038203 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 024 | 3727 | 116988 | SF | 0.031858 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 035 | 3811 | 89646 | SF | 0.042512 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 044 | 2421 | 66662 | SF | 0.036318 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 009 | 2369 | 55663 | SF | 0.04256 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 52A | 2781 | 47438 | SF | 0.058624 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 029 | 2329 | 47402 | SF | 0.049133 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 043 | 2365 | 45178 | SF | 0.052348 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 027 | 2426 | 42282 | SF | 0.057377 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 046 | 1608 | 42238 | SF | 0.03807 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 013 | 2133 | 40935 | SF | 0.052107 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 034 | 1640 | 35250 | SF | 0.046525 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 026 | 4692 | 33534 | SF | 0.13992 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 31A | 4210.25 | 31026 | SF | 0.1357 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 31B | 320.75 | 27367 | SF | 0.01172 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 054 | 1308 | 23837 | SF | 0.054873 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | S1N Bridge 3 | 2575 | 23315 | SF | 0.11044 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 015 | 2963 | 19930 | SF | 0.14867 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | S1N Bridge 8 | 2921 | 18980 | SF | 0.1539 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 030 | 1874 | 17957 | SF | 0.10436 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 023 | 3146 | 17497 | SF | 0.1798 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | S1N Bridge 2 | 2696 | 16601 | SF | 0.1624 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 018 | 1864 | 13581 | SF | 0.13725 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 17B | 1843 | 12711 | SF | 0.14499 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 20A | 2266 | 10666 | SF | 0.21245 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 049 | 1379 | 10527 | SF | 0.131 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | S1N Bridge 01C | 1424 | 9159 | SF | 0.15548 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | S1N Bridge 01B | 1406 | 8652 | SF | 0.16251 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 021 | 1862 | 7946 | SF | 0.23433 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 52B | 1179 | 7685 | SF | 0.15342 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 38A | 1265 | 6383 | SF | 0.19818 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 20B | 1174 | 6340 | SF | 0.18517 | Single Span |  | PC Girder | Single-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 045 | 1493 | 5413 | SF | 0.27582 | Multi-Span |  | PC Girder | Multi-Span | Widening/Rehab
IH 820 Southeast Connector | Bridge 016 | 1956 | 5358 | SF | 0.36506 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 032 | 967 | 4360 | SF | 0.22179 | Single Span |  | PC Girder | Single-Span | New/Reconstruct
IH 820 Southeast Connector | Bridge 041 | 1586 | 3646 | SF | 0.435 |  |  | Steel Girder | Multi-Span | Widening/Rehab
Ottawa LRT | PC Girder | 47300 | 193570 | SF | 0.24436 |  |  | PC Girder | Multi-Span | New/Reconstruct
Federal Way Link Extension | Design S2.01 - Elevated Guideway - Structure B | 22690.8 | 116016.5 | SF | 0.19558 |  |  | PC Girder | Multi-Span | New/Reconstruct
Federal Way Link Extension | Design S3.04 - Elevated Guideway - Structure G | 19540.9 | 96134 | SF | 0.20327 |  |  | CIP Girder | Multi-Span | New/Reconstruct
Federal Way Link Extension | Design S1.01 - Elevated Guideway - Structure A | 31022.599 | 82359 | SF | 0.37668 |  |  | PC Girder | Multi-Span | New/Reconstruct
I-15 Tropicana | D11 | 5819 | 46957 | SF | 0.12392 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
Federal Way Link Extension | Design S3.02 - Elevated Guideway - Structure E | 6590 | 34452 | SF | 0.19128 |  |  | CIP Girder | Multi-Span | New/Reconstruct
Federal Way Link Extension | Design S2.02B - Elevated Guideway - Structure C | 43403.25 | 39134 | SF | 1.1091 |  |  | PC Girder | Multi-Span | New/Reconstruct
Federal Way Link Extension | Design S3.03 - Elevated Guideway - Structure F | 2426.25 | 16052 | SF | 0.15115 |  |  | CIP Girder | Multi-Span | New/Reconstruct
Federal Way Link Extension | Design S3.01 - Elevated Guideway - Structure D | 4320.75 | 16045 | SF | 0.26929 |  |  | CIP Girder | Multi-Span | New/Reconstruct
Foothill Phase 2B1 LRT | LRT Lone Hill Ave | 4736 | 10674.33 | SF | 0.44368 |  |  | Box Girder | Multi-Span | New/Reconstruct
Foothill Phase 2B1 LRT | LRT Foothill Blvd-Grand Ave | 3910 | 8103.33 | SF | 0.48252 |  |  | Box Girder | Single-Span | New/Reconstruct
Foothill Phase 2B1 LRT | LRT Bonita Ave - Cataract Ave | 2206 | 7283.33 | SF | 0.30288 |  |  | Box Girder | Single-Span | New/Reconstruct
Foothill Phase 2B1 LRT | LRT U.S. State Route 66 | 5877 | 5781.48 | SF | 1.0165 |  |  | Box Girder | Multi-Span | New/Reconstruct
I-15 Tropicana | D14 | 3641 | 26805 | SF | 0.13583 | Single Span |  | PC Girder | Single-Span | New/Reconstruct
Foothill Phase 2B1 LRT | FRT San Dimas Wash | 2093 | 1900.5 | SF | 1.1013 |  |  | Steel Girder | Single-Span | New/Reconstruct
Foothill Phase 2B1 LRT | LRT Big Dalton Wash | 1978 | 1674 | SF | 1.1816 |  |  | Box Girder | Single-Span | New/Reconstruct
Foothill Phase 2B1 LRT | LRT Live Oak Channel | 1889 | 1550 | SF | 1.2187 |  |  | Box Girder | Single-Span | New/Reconstruct
Foothill Phase 2B1 LRT | FRT Big Dalton Wash | 1931 | 941.22 | SF | 2.0516 |  |  | Box Girder | Single-Span | New/Reconstruct
Foothill Phase 2B1 LRT | FRT Thompson Creek Channel | 1552 | 698.15 | SF | 2.223 |  |  | Box Girder | Single-Span | New/Reconstruct
Foothill Phase 2B1 LRT | FRT Live Oak Channel | 1171 | 530.47 | SF | 2.2075 |  |  | Box Girder | Single-Span | New/Reconstruct
Federal Way Link Extension | Design S1.03 - SR99 Bridge | 3372 | 24972 | SF | 0.13503 |  |  | PC Girder | Multi-Span | New/Reconstruct
I-15 Tropicana | D13 | 9398 | 18226 | SF | 0.51564 | Single Span |  | PC Girder | Single-Span | New/Reconstruct
I-17 Anthem | 2B4 | 3718 | 15442 | SF | 0.24077 | Multi-Span |  | PC Girder | Multi-Span | Widening/Rehab
I-15 Tropicana | D12 | 5094 | 13562 | SF | 0.37561 |  |  | Steel Girder | Multi-Span | New/Reconstruct
I-17 Anthem | 2B2 | 2150 | 13790 | SF | 0.15591 | Multi-Span |  | PC Girder | Multi-Span | New/Reconstruct
US 97 | Cooley Rd Bridge | 1923 | 8838.41 | SF | 0.21757 | Single Span |  | PC Girder | Single-Span | Unknown
US 97 | NB Bridge | 834 | 7779.43 | SF | 0.10721 | Single Span |  | PC Girder | Single-Span | Unknown
I-17 Anthem | 1B1 | 2637 | 13752 | SF | 0.19175 |  |  | CIP Slab | Multi-Span | Widening/Rehab
I-17 Anthem | 2B3 | 4265 | 9594 | SF | 0.44455 |  |  | Steel Girder | Multi-Span | Widening/Rehab
I-17 Anthem | 1B2 | 7106 | 7248 | SF | 0.98041 | Multi-Span |  | PC Girder | Multi-Span | Widening/Rehab
I-17 Anthem | 3B3 | 58 | 6553 | SF | 0.0088509 |  |  | Steel Girder | Multi-Span | Widening/Rehab
I-17 Anthem | 3B2 | 165.2 | 6528 | SF | 0.025306 |  |  | Steel Girder | Multi-Span | New/Reconstruct
I-17 Anthem | 2B1 | 2264 | 4599 | SF | 0.49228 |  |  | Steel Girder | Multi-Span | Widening/Rehab
I-17 Anthem | 3B1 | 1858 | 4462 | SF | 0.41641 |  |  | PC Deck | Multi-Span | Widening/Rehab
Del Rio | Bridge | 1421 | 4843 | SF | 0.29341 |  |  | PC Girder | Single-Span | New/Reconstruct
Ottawa LRT | Steel Girder | 3692 | 125680 | SF | 0.029376 |  |  | Steel Girder | Multi-Span | New/Reconstruct
Foothill Phase 2B1 LRT | LRT San Dimas Wash | 2787 | 2640 | SF | 1.0557 |  |  | PC Girder | Single-Span | New/Reconstruct
I-15 Tropicana | D15 | 2948 | 1440 | SF | 2.0472 | Single Span |  | PC Girder | Single-Span | New/Reconstruct
US 97 | Flyover Bridge | 6151 | 4766.54 | SF | 1.2905 |  |  | Box Girder | Single-Span | Unknown
Structure Name / Number | Location | FCT MHRs | eQTY | Unit | Production | Notes |  | Type | Span Arrangement | Scope
Awalua |  | 2152.112 | 6080 | SF | 0.35397 | Bridge - Precast Girder - Single Span |  | PC Girder | Multi-Span | New/Reconstruct
Lihau |  | 2442.1504 | 7636 | SF | 0.31982 | Bridge - Precast Girder - Single Span |  | PC Girder | Multi-Span | New/Reconstruct
Oluwalu |  | 3132.3896 | 11339 | SF | 0.27625 | Bridge - Precast Girder - Single Span |  | PC Girder | Multi-Span | New/Reconstruct
Upper Oluwalu |  | 1502.508 | 2595 | SF | 0.579 | Bridge - Precast Girder - Single Span |  | PC Girder | Multi-Span | New/Reconstruct
Luawai |  | 2370.2 | 7250 | SF | 0.32692 | Bridge - Precast Girder - Single Span |  | PC Girder | Multi-Span | New/Reconstruct
Ka'ili'ili |  | 2241.584 | 6560 | SF | 0.3417 | Bridge - Precast Girder - Single Span |  | PC Girder | Multi-Span | New/Reconstruct
Ukumehame |  | 2683.352 | 8930 | SF | 0.30049 | Bridge - Precast Girder - Single Span |  | PC Girder | Multi-Span | New/Reconstruct
Papalaua Viaduct |  | 4715.925 | 175750 | SF | 0.026833 | Bridge - Precast Girder - Multi Span |  | PC Girder | Multi-Span | New/Reconstruct
|  |  |  | SF |  |  |  |  | Multi-Span | Rehabilitation
|  |  |  | SF |  |  |  | PC Girder | Multi-Span | New/Reconstruct
|  |  |  | SF |  |  |  | PC Girder | Multi-Span | New/Reconstruct
|  |  |  | SF |  |  |  | Steel Girder | Single Span | New/Reconstruct
|  |  |  | SF |  |  |  | Steel Girder | Single Span | New/Reconstruct
|  |  |  | SF |  |  |  | PC Girder | Single Span | New/Reconstruct
|  |  |  | SF |  |  |  | PC Girder | Single Span | New/Reconstruct
Totals |  | 21240.221 | 226140 | SF

## MSRT
Miscellaneous Structure Design
eQTY: Spent MHRs of Roadway, Drainage and Traffic
Project | FCT MHRs | eQTY | Unit | Production | Applicable Job | Custom
IH 820 Southeast Connector | 19110 | 378295 | MHR | 0.050516 | Yes | 0.050516
BC Highway 1 | 738 | 6765 | MHR | 0.10909
Federal Way Link Extension | 9945 | 294035 | MHR | 0.033823
Foothill Phase 2B1 LRT | 12927 | 166681 | MHR | 0.077555
I-15 Tropicana | 4145 | 71064 | MHR | 0.058328 | Yes | 0.058328
I-17 Anthem | 5004 | 113381 | MHR | 0.044134 | Yes | 0.044134
264th Street Interchange | 1945 | 44396 | MHR | 0.04381 | Yes | 0.04381
Productions (Project Qty) |  | 42529.3725 | MHR | 0.064115 |  | 0.047799
Input / Output
Key Quantity (Column D) | 42529.3725
Total MHR (All Projects) | 2726.7831
Total MHR (Custom Projects) | 2032.8413
|  |  |  | Open | Custom
| Average | 0.059608 |  | 0.50632 | 0.037206
| Standard Dev. | 0.025848 |  | -0.19389 | 0.023506

## GEO
Geotechnical Design
eQTY: Count of Transportation Structures (EA)
Project | FCT MHRs | eQTY | Unit | Production | Applicable Job | Custom
IH 820 Southeast Connector | 47629 | 274 | EA | 173.8285 | Yes | 173.8285
BC Highway 1 | 1255 | 2 | EA | 627.5
BC Highway 5 | 4735 | 8 | EA | 591.875
Federal Way Link Extension | 33353 | 127 | EA | 262.622
Foothill Phase 2A LRT | 6797 | 19 | EA | 357.7368
Foothill Phase 2B1 LRT | 98819 | 99 | EA | 998.1717
I-15 Tropicana | 9508 | 33 | EA | 288.1212 | Yes | 288.1212
I-17 Anthem | 23572 | 110 | EA | 214.2909 | Yes | 214.2909
Tijuana River Barrier | 951 | 1 | EA | 951
US 97 | 2900 | 19 | EA | 152.6316 | Yes | 152.6316
264th Street Interchange | 7478 | 6 | EA | 1246.3333
Productions (Project Qty) |  | 12 | EA | 482.2567 |  | 207.7001
Input / Output
Key Quantity (Column D) | 12
Total MHR (All Projects) | 5787.0806
Total MHR (Custom Projects) | 2492.4014
|  |  |  | Open | Custom
| Average | 533.101 |  | 893.1471 | 217.5896
| Standard Dev. | 380.972 |  | -0.24801 | -0.018719

## SYS
Systems
eQTY: Track Alignment Length (TF)
Project | FCT MHRs | eQTY | Unit | Production | Applicable Job | Custom
Federal Way Link Extension | 153825 | 81688 | TF | 1.8831 | Yes | 1.8831
Foothill Phase 2A LRT | 39239 | 154899 | TF | 0.25332 | Yes | 0.25332
Foothill Phase 2B1 LRT | 88715 | 103233 | TF | 0.85937 | Yes | 0.85937
Ottawa LRT | 135270 | 167537 | TF | 0.8074
Productions (Project Qty) |  | 0 | TF | 0 |  | 0
Input / Output
Key Quantity (Column D) | 0
Total MHR (All Projects) | 0
Total MHR (Custom Projects) | 0
|  |  |  | Open | Custom
| Average | 0.95079 |  | 1241990026.2903 | 3960617645023161
| Standard Dev. | 0.67935 |  | -1.812 | -3.1212

## TRK
Track Design
eQTY: Track Alignment Length (TF)
Project | FCT MHRs | eQTY | Unit | Production | Applicable Job | Custom
Federal Way Link Extension | 55340 | 81688 | TF | 0.67746 | Yes | 0.67746
Foothill Phase 2A LRT | 8757 | 154899 | TF | 0.056534 | Yes | 0.056534
Foothill Phase 2B1 LRT | 6838 | 103233 | TF | 0.066239 | Yes | 0.066239
Ottawa LRT | 82275 | 167537 | TF | 0.49109
Productions (Project Qty) |  | 0 | TF | 0 |  | 0
Input / Output
Key Quantity (Column D) | 0
Total MHR (All Projects) | 0
Total MHR (Custom Projects) | 0
|  |  |  | Open | Custom
| Average | 0.32283 |  | 10125.8281 | 55284674262475608
| Standard Dev. | 0.31135 |  | -0.93049 | -3.4945

## ESDC
Engineering Services During Construction (ESDC)
eQTY: Anticipated Project Cost
Project | ESDC Cost | eQTY | Unit | Production | Applicable Job | Custom | Market | City, State | Country
IH 820 Southeast Connector | 23053.57 | 1938485.07 | K$ | 1.189% | Yes | 1.189% | Transportation, Highway | Fort Worth, TX | USA
Federal Way Link Extension | 21188.27 | 1376998.17 | K$ | 1.539% |  |  | Transit, Light Rail | Federal Way, WA | USA
Foothill Phase 2A LRT | 6232 | 470813.24 | K$ | 1.324% |  |  | Transit, Light Rail | San Dimas, CA | USA
Foothill Phase 2B1 LRT | 8894.15 | 836559.23 | K$ | 1.063% |  |  | Transit, Light Rail | San Dimas, CA | USA
Ottawa LRT | 52312.47 | 3691276.9 | K$ | 1.417% |  |  | Transit, Light Rail | Ottawa, ON | CAN
C-70 | 15995.5 | 1386636.6 | K$ | 1.154% | Yes | 1.154% | Transportation, Highway | Denver, CO | USA
I-25 T-REX | 9702.7 | 1144655.05 | K$ | 0.8477% | Yes | 0.8477% | Transportation, Highway | Denver, CO | USA
MoDOT 554 Bridges | 3418.31 | 405622.25 | K$ | 0.8427% |  |  | Transportation, Bridges | Jefferson City, CO | USA
Geneva Road | 347.6 | 41533.16 | K$ | 0.8369% | Yes | 0.8369% | Transportation, Highway | Orem, UT | USA
I-15 Corridor Reconstruction | 10453.15 | 1261222.85 | K$ | 0.8288% | Yes | 0.8288% | Transportation, Highway | Salt Lake City, UT | USA
SR-202 | 1276.02 | 155588.42 | K$ | 0.8201% | Yes | 0.8201% | Transportation, Highway | Phoenix, AZ | USA
DFW Connector | 6439.08 | 798052.8 | K$ | 0.8068% | Yes | 0.8068% | Transportation, Highway | Dallas, TX | USA
PCCP | 4673.55 | 697958.72 | K$ | 0.6696% |  |  | Water, Pump Station | New Orleans, LA | USA
Port Mann / Highway 1 | 21056.55 | 2388792.63 | K$ | 0.8815% |  |  | Transportation, Bridges | Vancoucer, BC | CAN
SR-520 Floating Bridge | 5789.17 | 642601.96 | K$ | 0.9009% |  |  | Transportation, Bridges | Seattle, WA | USA
Project Neon | 5539.52 | 611670.06 | K$ | 0.9056% | Yes | 0.9056% | Transportation, Highway | Las Vegas, NV | USA
Mountain View Corridor | 2199.24 | 229878.6 | K$ | 0.9567% | Yes | 0.9567% | Transportation, Highway | Salt Lake City, UT | USA
E-360 Bellevue to Redmond | 2290.37 | 236570.04 | K$ | 0.9682% | Yes | 0.9682% | Transportation, Highway | Seattle, WA | USA
Arlington Memorial Bridge | 1558.28 | 159839.66 | K$ | 0.9749% |  |  | Transportation, Bridges | Arlington, VA | USA
I-17 Anthem | 3210.57 | 320071.89 | K$ | 1.003% | Yes | 1.003% | Transportation, Highway | Phoenix, AZ | USA
Anthony Henday-Stony Plain | 1905.94 | 187397.98 | K$ | 1.017% | Yes | 1.017% | Transportation, Highway | Edmonton, AB | CAN
SH-183 Midtown Express | 9424.17 | 885258.97 | K$ | 1.065% | Yes | 1.065% | Transportation, Highway | Dallas, TX | USA
ICC-B | 5009.29 | 454376.58 | K$ | 1.102% | Yes | 1.102% | Transportation, Highway | Silver Springs, MD | USA
Pioneer Crossing | 2102.32 | 177230.46 | K$ | 1.186% | Yes | 1.186% | Transportation, Highway | Saratoga Springs, UT | USA
I-225 | 5263.24 | 424701.71 | K$ | 1.239% | Yes | 1.239% | Transportation, Highway | Denver, CO | USA
Farrington Guideway | 8764.95 | 684456.77 | K$ | 1.281% |  |  | Transit, Light Rail | Oahu, HI | USA
I-405 Renton to Bellevue | 8305.85 | 615922 | K$ | 1.349% | Yes | 1.349% | Transportation, Highway | Bellevue, WA | USA
Northwest Parkway | 2059.46 | 152435.75 | K$ | 1.351% | Yes | 1.351% | Transportation, Highway | Denver, CO | USA
I-15 Tropicana | 4650.13 | 328887.12 | K$ | 1.414% | Yes | 1.414% | Transportation, Highway | Las Vegas, NV | USA
Kamehameha Guideway | 6071.66 | 428252.13 | K$ | 1.418% |  |  | Transit, Light Rail | Honolulu, HI | USA
Turcot | 24752.38 | 1703515.46 | K$ | 1.453% | Yes | 1.453% | Transportation, Highway | Montreal, QC | CAN
Selmon Expressway Extension | 4154.99 | 253154.83 | K$ | 1.641% | Yes | 1.641% | Transportation, Highway | Tampa, FL | USA
Southwest Calgary Ring Road | 23281.64 | 1325890.67 | K$ | 1.756% | Yes | 1.756% | Transportation, Highway | Calgary, AB | USA
A-25 Bridge and Highway | 7407.17 | 420771.29 | K$ | 1.76% |  |  | Transportation, Bridges | Laval, QC | CAN
BART Warm Springs | 7824.31 | 428566.69 | K$ | 1.826% |  |  | Transit, Light Rail | Oakland, CA | USA
Sea-to-Sky Highway | 3379.41 | 590638.34 | K$ | 0.5722% | Yes | 0.5722% | Transportation, Highway | Vancoucer, BC | CAN
WMATA Yellow / Blue Lines | 991.97 | 191891.46 | K$ | 0.5169% |  |  | Transit, Light Rail | Alexandria, VA | USA
WMATA Blue / Green Lines | 1275.9 | 274719.66 | K$ | 0.4644% |  |  | Transit, Light Rail | Arlington, VA | USA
WMATA Orange / Silver Lines | 606.27 | 184682.6 | K$ | 0.3283% |  |  | Transit, Light Rail | Arlington, VA | USA
York Rapid Transit (D1) | 1061.44 | 165972.08 | K$ | 0.6395% |  |  | Transit, Bus | New Market, ON | CAN
York Rapid Transit (H2) | 744.47 | 162049.41 | K$ | 0.4594% |  |  | Transit, Bus | Vaughan, ON | CAN
I-405 Kirkland | 247.45 | 42990.54 | K$ | 0.5756% | Yes | 0.5756% | Transportation, Highway | Kirkland, WA | USA
I-440 Nashville Connector | 520.87 | 146656.02 | K$ | 0.3552% | Yes | 0.3552% | Transportation, Highway | Nashville, TN | USA
CHPE | 17183.59 | 1717328.8 | K$ | 1.001% |  |  | Power, Transmission | Buffalo, NY | USA
Productions (Project Qty) |  | 260869.5652 | K$ | 0.8796% |  | 0.9508%
Input / Output
Key Quantity (Column D) | 260869.5652
Total MHR (All Projects) | 2294.7346
Total MHR (Custom Projects) | 2480.4353
|  |  |  | Open | Custom
| Average | 0.010386 |  | 0.0010691 | 0.0020927
| Standard Dev. | 0.0038223 |  | 0.16899 | 0.12137

## TSCD
Temporary Structures & Construction Devices (TSCD)
eQTY: Anticipated Project Cost
Project | ESDC Cost | eQTY | Unit | Production | Applicable Job | Custom | Market | City, State | Country
IH 820 Southeast Connector | 7812.04 | 2006033.03 | K$ | 0.3894% | Yes | 0.3894% | Transportation, Highway | Fort Worth, TX | USA
E-130 LRT | 1955.98 | 820594.77 | K$ | 0.2384% |  |  | Transit, Light Rail | Seattle, WA | USA
Connect 4 | 1491.45 | 268033.92 | K$ | 0.5564% | Yes | 0.5564% | Transportation, Highway | Fort Worth, TX | USA
Foothill Phase 2B1 LRT | 809.18 | 836559.23 | K$ | 0.09673% |  |  | Transit, Light Rail | San Dimas, CA | USA
I-15 Tropicana | 830.59 | 368187.07 | K$ | 0.2256% | Yes | 0.2256% | Transportation, Highway | Las Vegas, NV | USA
C-70 | 7441.71 | 1290640.68 | K$ | 0.5766% | Yes | 0.5766% | Transportation, Highway | Denver, CO | USA
Turcot | 9542.25 | 1784779.8 | K$ | 0.5346% | Yes | 0.5346% | Transportation, Highway | Montreal, QB | CAN
Federal Way Link Extension | 1889.68 | 1403683.47 | K$ | 0.1346% |  |  | Transit, Light Rail | Federal Way, WA | USA
Southwest Calgary Ring Road | 2905.56 | 1310255.12 | K$ | 0.2218% | Yes | 0.2218% | Transportation, Highway | Calgary, AB | CAN
Goethals Bridge Replacement | 1935.06 | 1091231.6 | K$ | 0.1773% | Yes | 0.1773% | Transportation, Bridges | Staten Island, NY | USA
Midtown Express | 1552.51 | 914940.51 | K$ | 0.1697% | Yes | 0.1697% | Transportation, Highway | Irving, TX | USA
South Central LRT Extension | 592.66 | 823932.77 | K$ | 0.07193% |  |  | Transit, Light Rail | Phoenix, AZ | USA
Border West Expressway | 1858.64 | 691683.83 | K$ | 0.2687% | Yes | 0.2687% | Transportation, Highway | El Paso, TX | USA
Project Neon | 931.75 | 628296.99 | K$ | 0.1483% | Yes | 0.1483% | Transportation, Highway | Las Vegas, NV | USA
30 Crossing | 1551.47 | 497061.58 | K$ | 0.3121% | Yes | 0.3121% | Transportation, Bridges | Little Rock, AR | USA
I-225 Light Rail Corridor | 649.55 | 427748.52 | K$ | 0.1519% |  |  | Transit, Light Rail | Aurora, CO | USA
E-360 Bellevue to Redmond | 540.12 | 270974.68 | K$ | 0.1993% |  |  | Transit, Light Rail | Redmond, WA | USA
Selmon Expresseway Extension | 1955.92 | 262650 | K$ | 0.7447% | Yes | 0.7447% | Transportation, Highway | Tampa, FL | USA
Flyway 470 | 898.39 | 256515.18 | K$ | 0.3502% | Yes | 0.3502% | Transportation, Highway | Aurora, CO | USA
WMATA Station Rehab Contract 3 | 548.39 | 253581.12 | K$ | 0.2163% |  |  | Transit, Light Rail | Greenbelt, WA | USA
WMATA Station Rehab Contract 4 | 846.77 | 252986.82 | K$ | 0.3347% |  |  | Transit, Light Rail | Hyattsville, WA | USA
MVC 4100 South to SR-201 | 131.57 | 229983.74 | K$ | 0.05721% | Yes | 0.05721% | Transportation, Highway | West Valley City, UT | USA
Northwest Phase 2 LRT Extension | 181.77 | 214449.31 | K$ | 0.08476% |  |  | Transit, Light Rail | Phoenix, AZ | USA
Tlicho All-Season Road | 216.41 | 183706.28 | K$ | 0.1178% | Yes | 0.1178% | Transportation, Highway | Whati, ON | USA
WMATA Orange / Silver Line | 464.64 | 178931.16 | K$ | 0.2597% |  |  | Transit, Light Rail | Arlington, VA | USA
WMATA Yellow Line Rehab | 920.05 | 175655.73 | K$ | 0.5238% |  |  | Transit, Light Rail | Washington, DC | USA
I-10 Capital Corridor | 1776.12 | 159847.91 | K$ | 1.111% | Yes | 1.111% | Transportation, Highway | Baton Rouge, LA | USA
Nashville Connector | 361.46 | 148878.92 | K$ | 0.2428% | Yes | 0.2428% | Transportation, Bridges | Nashville, TN | USA
Moosejaw | 759.58 | 148722.83 | K$ | 0.5107% | Yes | 0.5107% | Transporation, Highway | Virginia, MT | USA
Big Thompson | 235.58 | 146038.94 | K$ | 0.1613% | Yes | 0.1613% | Transportation, Highway | Loveland, CO | USA
Kingston Third Crossing | 1140.54 | 144336.5 | K$ | 0.7902% | Yes | 0.7902% | Transportation, Bridges | Kingston, ON | USA
Porter Road | 770.65 | 112340.79 | K$ | 0.686% | Yes | 0.686% | Transportation, Highway | Springdale, TX | USA
SR 99 Alaskan Way Viaduct Demo | 1101.92 | 98750.74 | K$ | 1.116% |  |  | Transportation, Bridges | Seattle, WA | USA
LA 1: Port Allen Canal Bridge | 104.12 | 96311.72 | K$ | 0.1081% |  |  | Transportation, Bridges | Port Allen, LA | USA
CTA Congress Track Phase 1 | 65.34 | 89697.94 | K$ | 0.07284% |  |  | Transit, Light Rail | Chicago, IL | USA
Fort Smith | 313.47 | 82226.01 | K$ | 0.3812% |  |  | Transportation, Highway | Fort Smith, TX | USA
I-40 Gorge Bridge #171 | 238.23 | 81544.24 | K$ | 0.2921% |  |  | Transportation, Bridges | Asheville, NC | USA
Jack-Stone 10 | 238.23 | 75197.11 | K$ | 0.3168% |  |  | Transportation, Highway | Little Rock, AR | USA
Camp Hall Rail Phase 2 | 527.05 | 65946.73 | K$ | 0.7992% |  |  | Transit, Heavy Rail | Ridgeville, SC | USA
I-15 Virgin River Bridge #1 | 573.95 | 55959.52 | K$ | 1.026% |  |  | Transportation, Bridges | Littlefield, AZ | USA
12/80 Crossing | 187.98 | 54936.65 | K$ | 0.3422% |  |  | Transportation, Highway | Suisun City, CA | USA
Broadway Bridge | 808.9 | 52838.52 | K$ | 1.531% |  |  | Transportation, Bridges | Nashville, TN | USA
Nashville I-40 Fast Fix 8 | 348.92 | 50452.65 | K$ | 0.6916% |  |  | Transportation, Bridges | Nashville, TN | USA
MemFix 4 | 377.9 | 49375.47 | K$ | 0.7654% |  |  | Transportation, Bridges | Memphis, TN | USA
Nolichucky Bridges | 201.29 | 49244.86 | K$ | 0.4088% |  |  | Transportation, Bridges | Erwin, TN | USA
Stone Myers Parkway | 139.24 | 47857.5 | K$ | 0.2909% |  |  | Transportation, Highway | Irving, TX | USA
Coastal 29 Fish Passage 2A | 119.67 | 42266.18 | K$ | 0.2831% |  |  | Fish Passage | Amanda Park, WA | USA
Chesapeake Bay Bridge Security | 129.45 | 38421.81 | K$ | 0.3369% |  |  | Transportation, Bridges | Stevensville, MD | USA
Glenn Highway Phase 2 | 183.57 | 37934.53 | K$ | 0.4839% |  |  | Transportation, Highway | Anchorage, AK | USA
I-210 Prien Lake | 197.2 | 35186.61 | K$ | 0.5604% |  |  | Transportation, Highway | Prien, LA | USA
Lonoke Bridges | 204.04 | 29205.96 | K$ | 0.6986% |  |  | Transportation, Bridges | Lonoke, TX | USA
TVTA VN89/VN30 Tower Bases | 191.04 | 28548.5 | K$ | 0.6692% |  |  | Transportation, Bridges | New York, NY | USA
Coastal 29 Fish Passage 1 | 46.05 | 27597.84 | K$ | 0.1669% |  |  | Fish Passage | Amanda Park, WA | USA
Brooklyn Bridge Hazard Mitigation | 161.26 | 27486.2 | K$ | 0.5867% |  |  | Transportation, Bridges | New York, NY | USA
Coastal 29 Fish Passage 4 | 28.96 | 27441.11 | K$ | 0.1055% |  |  | Fish Passage | Hoquiam, WA | USA
NMDOT Mora County | 63.69 | 24864.19 | K$ | 0.2562% |  |  | Transportation, Highway | Guadalupita | USA
Blue Oval Memphis Megasite | 61.73 | 24549.23 | K$ | 0.2515% |  |  | Transportation, Highway | Stanton, TN | USA
Stagecoach Ramps | 25.46 | 22054.5 | K$ | 0.1154% |  |  | Transportation, Highway | Little Rock, AR | USA
Crystal Springs Bridge | 169.96 | 21752.48 | K$ | 0.7813% |  |  | Transportation, Bridges | San Mateo, CA | USA
CFRC Capital Improvements | 103.47 | 20964.44 | K$ | 0.4936% |  |  | Transit, Heavy Rail | Kissimmee, FL | USA
MP09 Tower Elevators & Rehab | 177.1 | 20016.45 | K$ | 0.8848% |  |  | Transportation, Bridges | New York, NY | USA
Toronto Union Station | 90.6 | 19180.89 | K$ | 0.4723% |  |  | Transit, Heavy Rail | Toronto, ON | CAN
Kake Access Road | 53.17 | 18448.83 | K$ | 0.2882% |  |  | Transportation, Highway | Petersburg, HI | USA
Unionport Foundations | 188.78 | 17435.91 | K$ | 1.083% |  |  | Transportation, Bridges | New York, NY | USA
Dewey Beach Bridges | 157.59 | 17154.81 | K$ | 0.9186% |  |  | Transportation, Bridges | Rehoboth, DE | USA
Metropolitan Ave Bascule Repairs | 59.67 | 15272.79 | K$ | 0.3907% |  |  | Transportation, Bridges | New York, NY | USA
Railroad Ave Extension | 81.67 | 13816.58 | K$ | 0.5911% |  |  | Transportation, Highway | Hanahan, SC | USA
Garland County | 25.53 | 12820.18 | K$ | 0.1991% |  |  | Transportation, Highway | Hot Springs | USA
SR530/Trafton Creek Fish Passage | 31.57 | 12819.77 | K$ | 0.2463% |  |  | Fish Passage | Arlington, VA | USA
STC Landside Piles | 160.16 | 12632.25 | K$ | 1.268% |  |  | Buildings | Orlando, FL | USA
CCH Kailua Roundabout | 27.51 | 11436.26 | K$ | 0.2406% |  |  | Transportation, Highway | Kailua, HI | USA
SFOBB Foundation Removal | 154.29 | 11349.37 | K$ | 1.359% |  |  | Transportation, Bridges | Oakland, CA | USA
Camino Real | 57.63 | 10973.19 | K$ | 0.5252% |  |  | Transportation, Highway | Boca Raton, LA | USA
Kawela / Nanahu Stream Bridge | 31.06 | 10110.5 | K$ | 0.3072% |  |  | Transportation, Bridges | Kahuku, HI | USA
Okolona Pass | 68.56 | 9504.39 | K$ | 0.7214% |  |  | Transportation, Highway | Okolona, HI | USA
Carrol Ave Bridge Rehab | 167.37 | 9254.73 | K$ | 1.808% |  |  | Transportation, Bridges | Takoma Park, MD | USA
Clark Fork Bridge | 117.31 | 9119.2 | K$ | 1.286% |  |  | Transportation, Bridges | Missoula | USA
SR89 Truckee River Bridge Project | 70.64 | 7057.08 | K$ | 1.001% |  |  | Transportation, Bridges | Alpine Meadows | USA
De Soto II | 80.17 | 6858.07 | K$ | 1.169% |  |  | Transportation, Bridges | Memphis, TN | USA
Murphy Road Bridge Replacement | 26.9 | 6811.3 | K$ | 0.3949% |  |  | Transportation, Bridges | Palm City | USA
Rio San Juan | 109.71 | 6632.32 | K$ | 1.654% |  |  | Transportation, Highway | Farmington, CA | USA
I-75 Bridge Rehabilitation | 27.01 | 6073.34 | K$ | 0.4447% |  |  | Transportation, Bridges | Kennesaw | USA
SR 117 Bridge over Moncrief Creek | 49.69 | 5987.03 | K$ | 0.83% |  |  | Transportation, Bridges | Jacksonville, TN | USA
I-40 Hernando DeSoto Repairs | 35.05 | 5743.38 | K$ | 0.6103% |  |  | Transportation, Bridges | Memphis, TN | USA
Butte Highway 11 | 106.88 | 5363.53 | K$ | 1.993% |  |  | Transportation, Highway | Butte, WY | USA
HDOT Kapalama Wharf | 656.39 | 316176.62 | K$ | 0.2076% |  |  | Marine | Honolulu, HI | USA
Conneticut State Pier | 1018 | 283210.74 | K$ | 0.3594% |  |  | Marine | New London, CT | USA
NAVFAC Bremerton Seismic | 1521.4 | 201369.3 | K$ | 0.7555% |  |  | Marine | Bremerton, WA | USA
Fairview Phase 2 Expansion | 117.68 | 131927.35 | K$ | 0.0892% |  |  | Marine | Prince Rupert, ON | CAN
MOTCO Pier 2 Replacement | 720.46 | 90059.55 | K$ | 0.8% |  |  | Marine | Concord, CA | USA
BAEJSR Shiplift Drydock | 585.15 | 77329.42 | K$ | 0.7567% |  |  | Marine | Jacksonville, FL | USA
Plaquemines LNG Marine Ph 2 | 230.73 | 72507.27 | K$ | 0.3182% |  |  | Marine | Port Sulphur, LA | USA
Empire Floodgate | 315.59 | 71234.3 | K$ | 0.443% |  |  | Marine | Empire, LA | USA
Dallas Floodway 277K Levee Raise | 224.15 | 51318.87 | K$ | 0.4368% |  |  | Marine | Dallas, TX | USA
Permanente Creek McKelvey Park | 231.5 | 40306.86 | K$ | 0.5743% |  |  | Marine | Mountain View, CA | USA
West Container Yard Expansion | 15.53 | 32619.62 | K$ | 0.04761% |  |  | Marine | Greer, SC | USA
Southport Turning Notch | 40.66 | 24423.95 | K$ | 0.1665% |  |  | Marine | Hollywood, FL | USA
C&O Canal Historic Stone Wall | 139.65 | 15871.7 | K$ | 0.8799% |  |  | Marine | Williamsport, MD | USA
St. Paul Harbor Breakwater | 12.58 | 14615.16 | K$ | 0.08608% |  |  | Marine | St. Paul, WA | USA
Ponce Inlet North Jetty | 67.71 | 13741.99 | K$ | 0.4927% |  |  | Marine | Ponce Inlet, FL | USA
LNYBL Cross Bay Resiliency | 75.83 | 11953.79 | K$ | 0.6344% |  |  | Marine | New York, NY | USA
SYC Ph 1 Marine Bulkhead | 9.87 | 10002.61 | K$ | 0.09867% |  |  | Marine | Savannah, GA | USA
Berryessa Flood Control Impvmt | 17.16 | 5643.95 | K$ | 0.304% |  |  | Marine | Milpitas, CA | USA
GPA ERT Dock Refurbishments | 4.77 | 4170.36 | K$ | 0.1144% |  |  | Marine | Brunswick, GA | USA
Jaxport Berth 22 Dolphins | 60.1 | 3896.81 | K$ | 1.542% |  |  | Marine | Jacksonville, FL | USA
Vulcan MD Quarry Bulkhead | 42 | 3375.52 | K$ | 1.244% |  |  | Marine | Hacre de Grace, ON | CAN
GPA Mayor's Point Fender System | 9.97 | 2898.49 | K$ | 0.344% |  |  | Marine | Brunswick, GA | USA
Waikiki Seawall Improvements | 4.92 | 1405.45 | K$ | 0.3501% |  |  | Marine | Honolulu, HI | USA
Doral Gravity Wall | 2.07 | 477.05 | K$ | 0.4339% |  |  | Marine | Doral, FL | USA
Productions (Project Qty) |  | 260869.5652 | K$ | 0.2867% |  | 0.3255%
Input / Output
Key Quantity (Column D) | 260869.5652
Total MHR (All Projects) | 747.8593
Total MHR (Custom Projects) | 849.2406
|  |  |  | Open | Custom
| Average | 0.0052075 |  | 0.02454 | 0.010167
| Standard Dev. | 0.0041116 |  | -0.17216 | -0.091309

## Notes
Trendline Equations:
https://www.ablebits.com/office-addins-blog/excel-trendline-types-equations-formulas/#logarithmic-trendline

## Dropdowns
Digital Engineering: Complexity
Low
Low-Med
Med
Med-High
High
Allowable Multiplier | 2.85
Hourly Composite Rate | 64.5